## Task Sheet
Names | Monday (11/2/2019) | Thursday (14/2/2019) | Sunday (17/2/2019)
Youssef | Create new Course | View Course Details | Implement Routing
Hala | Create Grade Sheet | View Grade Sheet For Instructor | View Grade Sheet For Student
Yara | Create Attendence | View Attendence Sheet For Instrcutor | View Attendence Sheet For Student
Fathy | Authorization Filter | Create Quiz | View Quiz
Abanoub | Attachment Upload & Download & Video Frame & Rich Text Editor Example | Add Attachments (Upload) for Course and View Attachment | Add Videos (Youtube) to Course and View Video in Video Frame
Manar | User List | User Profile
Notes | These tasks should be implemented by Monday (EoD) End of Day | On Thursday, Starting Implementing These tasks according to Technical Design | On Monday Start working on These Tasks and to be finished by Tuesday EoD
| Starting from Tuesday working on Next Tasks Technical Design. Check Sheet 2 To be Done by EoD | These Tasks to be Done by Friday EoD and Reviewed by me on Friday | Checking the Comments and Bugs from Last Tasksand waiting from Comments and Bugs of new Tasks
| Wednesday for fixing comments and bugs of Monday Tasks and Check the Comments of Technical Designs | On Saturday Start working on Technical Design for new Tasks and to be finished by EoD
On Sunday Start working on Comments and Bugs

## Technical Design Requirement
Requirement | Column1 | Column2 | Column3 | Column4 | Column5
What is the name of Angular Component? | create-new-course | course/components/create-new-course
What are the Rest Services Information? | Function Name 1. LookupRes.findAllCategories() 2. LookupRes.findAllCorTypes() 3. CourseRes.createNewCourse() | REST PATH 1. /lookup/categories/ 2. /lookup/corTypes/ 3. /course/new/ | METHOD 1. GET 2. GET 3. POST | Return Data 1. List<Category> 2. List<CorType> 3. void | Parameter 1. None 2. None 3. CourseDTO
Functions to be Implemented in Spring Service Layer | CourseSer.insertNewCourse() Steps: 1. Generate CourseID 2. Validate The User is Instructor
Functions to be Implemented in Spring Repository Layer + Query | CourseRep.insertNewCourse() UserRep.checkUserIsInstructor()
What are the Modals (Frontend & Backend) Needed and Their Attributes | Class Category int id String labelEN | Class CourseDTO int id String name int corTypeID
Angular Service Needed | course.service lookup.service | course/shared/course.service.ts layout/shared/services/lookup.service.ts
Draw Design Layout
Database Design & Relations(Tables Related for the Task only) | auth_user course